## WBS
WBS ID | Work Package / Task | Description | Deliverable / Output | Status
1.0 | Requirements Engineering | Define and document system requirements. | Requirements baseline | Completed
1.1 | Identify Stakeholders and Actors | Identify Student Founder, Campaign Backer, Faculty Committee, and Payment Gateway. | Actor list | Completed
1.2 | Define Functional Requirements | Document FR-001 to FR-005. | FR table | Completed
1.3 | Define Non-Functional Requirements | Document NFR-001 and NFR-002. | NFR table | Completed
1.4 | Create Requirements Traceability Matrix | Map requirements to use cases, design flows, acceptance criteria, and tests. | RTM.xlsx | Completed
2.0 | System Analysis and Design | Model the system behavior and structure. | Design baseline | In Progress
2.1 | Create Use Case Diagram | Model actors, primary use cases, include and extend relationships. | Use Case Diagram | Completed
2.2 | Create Activity Diagram | Model UC-05 release-tranche flow and alternate paths. | Activity Diagram | Completed
2.3 | Design System Architecture | Define presentation, application/service, data, and external payment gateway components. | Architecture Diagram | Planned
3.0 | Software Documentation | Prepare project documentation. | Documentation set | In Progress
3.1 | Prepare SRS | Document purpose, scope, requirements, use cases, architecture overview, and traceability. | SRS.pdf | Completed
3.2 | Prepare WBS | Break project work into manageable packages and tasks. | WBS.xlsx | Completed
4.0 | Implementation | Implement core crowdfunding platform functionality. | Working system | Planned
4.1 | Campaign Creation | Implement campaign goal, deadline, milestones, rewards, and eligibility validation. | Campaign module | Planned
4.2 | Campaign Browsing and Rewards | Allow backers to browse active campaigns and select reward tiers. | Campaign browsing module | Planned
4.3 | Pledge Management | Accept qualifying pledges and integrate tokenized payment processing. | Pledge module | Planned
4.4 | Milestone Review | Allow faculty reviewers to approve, reject, or request more information with comments. | Review module | Planned
4.5 | Tranche Disbursement | Release approved tranches through the Payment Gateway and record outcomes. | Disbursement module | Planned
4.6 | Cancellation and Refund | Cancel unsuccessful campaigns and initiate refunds after deadline. | Refund module | Planned
5.0 | Testing and Quality Assurance | Verify functional and non-functional behavior. | Test evidence | Planned
5.1 | Functional Testing | Test FR-001 to FR-005. | Functional test results | Planned
5.2 | Non-Functional Verification | Verify payment security approach, pledge latency target, uptime and durability design. | NFR evidence | Planned
5.3 | Bug Identification and Fix | Use AI/vibe coding to diagnose and patch an identified defect. | Bug-fix evidence | Planned
5.4 | Retesting | Run the affected test again after the patch. | Retest evidence | Planned
6.0 | Project Management and Tooling | Maintain project repositories and issue tracking. | Project-management evidence | In Progress
6.1 | GitHub Repository Setup | Organize project deliverables into the required folder structure. | GitHub repository | Completed
6.2 | JIRA Project Setup | Create project, issues, and workflow board for project work. | JIRA project/board | Planned
6.3 | Project Evidence Capture | Capture screenshots showing the configured GitHub/JIRA project-management artifacts required by the lab. | Screenshots | Planned

## WBS Summary
Category | Main Output
Requirements Engineering | Requirements table + RTM
System Analysis and Design | Use Case Diagram + Activity Diagram + Architecture Diagram
Software Documentation | SRS + WBS
Implementation | Crowdfunding platform modules
Testing and QA | Test results + bug fix + retest evidence
Project Management | GitHub/JIRA evidence